## README
Project Budget Calculator
PURPOSE | Calculates the Budgeted balance of each project and phases it over the remaining months of the project.
FORMULAS
Budgeted | Budgeted = Contracted Budget − WIP to date (the sum of WIP logged in months up to and including the Current Month).
Phased Budgeted | Budgeted is spread only over the project months AFTER the Current Month, using that project's phasing weights for those months, renormalised to 1.0.
Phased Budgeted (month k) = Budgeted × weight(k) ÷ Σ weights of remaining months.
Weights | Enter raw weights (e.g. 1,2,2,2,2). They don't need to sum to 1. If a project has no weights at all, every month gets an equal weight.
Example (from the slide) | Contract 10,000. 5 months, weights 1:2:2:2:2. 1,000 of WIP logged in month I (the current month).
→ Budgeted = 9,000, phased over months II–V (weights 2:2:2:2 → 25% each) = 2,250 per month.
SHEETS
Projects | Project ∑ table (page 1). Holds the global Current Month field. Add a project by filling in the next empty row. Use the header filter buttons to filter.
Phasing | Raw phasing weights per project, month 1–24 of the project. Also shows the weights normalised to 1.0 over the full duration.
WIP Log | Monthly WIP actuals per project on the calendar timeline. Only months ≤ Current Month count towards WIP to date.
Project Page | Page 2: pick a project from the dropdown to see its details, month-by-month phasing and chart (the "visualize" view).
Timeline | Page 3: Gantt-style view of every project. Each cell shows the WIP actual (≤ Current Month) or the Phased Budgeted (after it).
Aggregator | Page 4: Σ WIP + Σ Phased Budgeted per month against the manual TRM input, with a chart and calendar-year totals.
Phased Budget | Calculation grid (no inputs): Phased Budgeted per project per calendar month.
HOW TO USE
Yellow cells | Key inputs: Current Month, Timeline Start, the TRM row and the project selector.
Blue text | Hard-coded inputs: project fields, weights, WIP amounts. Black text = formulas. Green text = links to another sheet.
Light yellow grids | Input grids on Phasing and WIP Log. Grey cells there are outside the project's duration or window.
Monthly routine | 1) Log the month's WIP on WIP Log. 2) Move Current Month forward one month on Projects. Everything recalculates.
Status column | Projects!N flags problems: WIP above contract, no remaining months left to phase the budget into, missing fields, etc.
LIMITS & ASSUMPTIONS
Capacity | 50 projects, durations up to 24 months, calendar timeline of 36 months from Timeline Start (default Jan 2026 – Dec 2028).
Timeline Start | Change it only before logging WIP: the WIP Log columns are tied to calendar months, so moving the start shifts those columns.
Months | Starting Month and Current Month are compared by year and month only (the day is ignored).
Units | All amounts are in one currency unit (enter 10000 for 10k). No currency symbol is applied.
TRM | Monthly comparison target, entered manually on the Aggregator sheet (per user).
Annual totals | Calendar years (Jan–Dec), WIP actuals + Phased Budgeted.
Source | Logic from "Revenue_Forecast_Calculator.pptx", with the user's clarifications from 2026-10-06.

## Projects
Project ∑ Table
Current Month |  | 2026-10-01 | Months up to and including this month are actuals (WIP). Later months are forecast (Phased Budgeted).
Timeline Start |  | 2026-01-01 | First month of the 36-month calendar timeline. Change it only before logging WIP.
# | Project Name | Engagement Manager | Starting Month | Duration (months) | End Month | Contracted Budget | WIP to Date | Budgeted (Contract − WIP) | Remaining Months | Phased Budgeted – Next Month | Phased Budgeted – Rest of Current Year | Current-Year Forecast (WIP + Phased) | Status
1 | Example Project (slide) | J. Doe | 2026-10-01 | 5 | 2027-02-01 | 10000 | 1000 | 9000 | 4 | 2250 | 4500 | 5500 | OK
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
| TOTAL |  |  |  |  | 10000 | 1000 | 9000 |  | 2250 | 4500 | 5500 | 0 project(s) need attention
Formulas:
End Month = IF(OR([Starting Month]="",[Duration (months)]=""),"",EDATE([Starting Month],[Duration (months)]-1))
Note on B6: Example row from the slide: contract 10k, weights 1:2:2:2:2, 1k of WIP in month I. Overwrite or delete it.
Note on C2: Default: October 2026 (the build date). Move it forward each month.
Note on C3: Default: Jan 2026. The timeline is 36 months long.

## Phasing
Phasing Weights
[7 empty] | month index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Enter raw weights in the yellow cells (month 1 = Starting Month). They are renormalised to 1.0 automatically. Leave a row blank for equal weights.
[8 empty] | 1: RAW WEIGHTS (input) → | NORMALISED WEIGHTS, FULL DURATION (Σ = 1.0) →
# | Project Name | Duration | Weights entered | Σ weights (full duration) | First remaining month # | Σ weights (remaining months) | Non-zero weights beyond duration | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | Check Σ
1 | Example Project (slide) | 5 | 5 | 9 | 2 | 8 | 0 | 1: 1; 2: 2; 3: 2; 4: 2; 5: 2 | 11.11% | 22.22% | 22.22% | 22.22% | 22.22% | [19 empty] | 100%
2 |  |  | 0 | 0 | 1 | 0 | 0
3 |  |  | 0 | 0 | 1 | 0 | 0
4 |  |  | 0 | 0 | 1 | 0 | 0
5 |  |  | 0 | 0 | 1 | 0 | 0
6 |  |  | 0 | 0 | 1 | 0 | 0
7 |  |  | 0 | 0 | 1 | 0 | 0
8 |  |  | 0 | 0 | 1 | 0 | 0
9 |  |  | 0 | 0 | 1 | 0 | 0
10 |  |  | 0 | 0 | 1 | 0 | 0
11 |  |  | 0 | 0 | 1 | 0 | 0
12 |  |  | 0 | 0 | 1 | 0 | 0
13 |  |  | 0 | 0 | 1 | 0 | 0
14 |  |  | 0 | 0 | 1 | 0 | 0
15 |  |  | 0 | 0 | 1 | 0 | 0
16 |  |  | 0 | 0 | 1 | 0 | 0
17 |  |  | 0 | 0 | 1 | 0 | 0
18 |  |  | 0 | 0 | 1 | 0 | 0
19 |  |  | 0 | 0 | 1 | 0 | 0
20 |  |  | 0 | 0 | 1 | 0 | 0
21 |  |  | 0 | 0 | 1 | 0 | 0
22 |  |  | 0 | 0 | 1 | 0 | 0
23 |  |  | 0 | 0 | 1 | 0 | 0
24 |  |  | 0 | 0 | 1 | 0 | 0
25 |  |  | 0 | 0 | 1 | 0 | 0
26 |  |  | 0 | 0 | 1 | 0 | 0
27 |  |  | 0 | 0 | 1 | 0 | 0
28 |  |  | 0 | 0 | 1 | 0 | 0
29 |  |  | 0 | 0 | 1 | 0 | 0
30 |  |  | 0 | 0 | 1 | 0 | 0
31 |  |  | 0 | 0 | 1 | 0 | 0
32 |  |  | 0 | 0 | 1 | 0 | 0
33 |  |  | 0 | 0 | 1 | 0 | 0
34 |  |  | 0 | 0 | 1 | 0 | 0
35 |  |  | 0 | 0 | 1 | 0 | 0
36 |  |  | 0 | 0 | 1 | 0 | 0
37 |  |  | 0 | 0 | 1 | 0 | 0
38 |  |  | 0 | 0 | 1 | 0 | 0
39 |  |  | 0 | 0 | 1 | 0 | 0
40 |  |  | 0 | 0 | 1 | 0 | 0
41 |  |  | 0 | 0 | 1 | 0 | 0
42 |  |  | 0 | 0 | 1 | 0 | 0
43 |  |  | 0 | 0 | 1 | 0 | 0
44 |  |  | 0 | 0 | 1 | 0 | 0
45 |  |  | 0 | 0 | 1 | 0 | 0
46 |  |  | 0 | 0 | 1 | 0 | 0
47 |  |  | 0 | 0 | 1 | 0 | 0
48 |  |  | 0 | 0 | 1 | 0 | 0
49 |  |  | 0 | 0 | 1 | 0 | 0
50 |  |  | 0 | 0 | 1 | 0 | 0

## WIP Log
WIP Log (monthly actuals)
Enter the WIP actual for each project and month. Only months up to and including the Current Month count; later months are ignored.
|  |  | actual | actual | actual | actual | actual | actual | actual | actual | actual | actual | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future | future
# | Project Name | WIP to Date (≤ Current Month) | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
1 | Example Project (slide) | 1000 | 2026-10-01: 1000
2 |  | 0
3 |  | 0
4 |  | 0
5 |  | 0
6 |  | 0
7 |  | 0
8 |  | 0
9 |  | 0
10 |  | 0
11 |  | 0
12 |  | 0
13 |  | 0
14 |  | 0
15 |  | 0
16 |  | 0
17 |  | 0
18 |  | 0
19 |  | 0
20 |  | 0
21 |  | 0
22 |  | 0
23 |  | 0
24 |  | 0
25 |  | 0
26 |  | 0
27 |  | 0
28 |  | 0
29 |  | 0
30 |  | 0
31 |  | 0
32 |  | 0
33 |  | 0
34 |  | 0
35 |  | 0
36 |  | 0
37 |  | 0
38 |  | 0
39 |  | 0
40 |  | 0
41 |  | 0
42 |  | 0
43 |  | 0
44 |  | 0
45 |  | 0
46 |  | 0
47 |  | 0
48 |  | 0
49 |  | 0
50 |  | 0
| TOTAL | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Page
Project Page | [8 empty] | row | 1
Select project ▸ | Example Project (slide)
Engagement Manager | J. Doe
Starting Month | 2026-10-01
Duration (months) | 5
End Month | 2027-02-01
Contracted Budget | 10000
WIP to Date | 1000
Budgeted (Contract − WIP) | 9000
Remaining Months | 4
Status | OK
Project Month | Calendar Month | Raw Weight | Plan Weight (Σ=1) | Original Plan (Contract × weight) | WIP Actual | Phased Budgeted | Total (WIP + Phased) | Actual / Forecast
1 | 2026-10-01 | 1 | 11.11% | 1111.1111 | 1000 | 0 | 1000 | Actual
2 | 2026-11-01 | 2 | 22.22% | 2222.2222 | 0 | 2250 | 2250 | Forecast
3 | 2026-12-01 | 2 | 22.22% | 2222.2222 | 0 | 2250 | 2250 | Forecast
4 | 2027-01-01 | 2 | 22.22% | 2222.2222 | 0 | 2250 | 2250 | Forecast
5 | 2027-02-01 | 2 | 22.22% | 2222.2222 | 0 | 2250 | 2250 | Forecast
TOTAL |  |  | 100% | 10000 | 1000 | 9000 | 10000
Check: Total = Contract | [6 empty] | ✓ ties
Formulas:
Calendar Month = IF([Project Month]="","",EDATE(B6,[Project Month]-1))

## Timeline
Project Timeline
Dark orange = WIP actual (≤ Current Month). Light orange = Phased Budgeted. The bordered column is the Current Month.
# | Project Name | Engagement Manager | Start | End | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
1 | Example Project (slide) | J. Doe | 2026-10-01 | 2027-02-01 | [9 empty] | 1000 | 2250 | 2250 | 2250 | 2250
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Aggregator
Aggregator
Σ WIP actuals (≤ Current Month) + Σ Phased Budgeted (after it) per month, against TRM. Enter TRM in the yellow column.
Month | Year | Σ WIP (actual) | Σ Phased Budgeted | Total (WIP + Phased) | TRM (input) | Variance (Total − TRM) | Annual (calendar year)
2026-01-01 | 2026 | 0 | 0 | 0 |  |  | Year | Σ WIP (actual) | Σ Phased Budget | WIP + Phased Budget | TRM | Variance
2026-02-01 | 2026 | 0 | 0 | 0 |  |  | 2026 | 1000 | 4500 | 5500 | 0 | 5500
2026-03-01 | 2026 | 0 | 0 | 0 |  |  | 2027 | 0 | 4500 | 4500 | 0 | 4500
2026-04-01 | 2026 | 0 | 0 | 0 |  |  | 2028 | 0 | 0 | 0 | 0 | 0
2026-05-01 | 2026 | 0 | 0 | 0 |  |  | Total | 1000 | 9000 | 10000 | 0 | 10000
2026-06-01 | 2026 | 0 | 0 | 0
2026-07-01 | 2026 | 0 | 0 | 0 |  |  | Reconciliation
2026-08-01 | 2026 | 0 | 0 | 0 |  |  | Σ Contracted Budget |  |  | 10000
2026-09-01 | 2026 | 0 | 0 | 0 |  |  | Σ WIP to date (all projects) |  |  | 1000
2026-10-01 | 2026 | 1000 | 0 | 1000 |  |  | Σ Phased Budgeted (on timeline) |  |  | 9000
2026-11-01 | 2026 | 0 | 2250 | 2250 |  |  | Difference (unphased / off-timeline) |  |  | 0 | ✓ fully phased
2026-12-01 | 2026 | 0 | 2250 | 2250
2027-01-01 | 2027 | 0 | 2250 | 2250
2027-02-01 | 2027 | 0 | 2250 | 2250
2027-03-01 | 2027 | 0 | 0 | 0
2027-04-01 | 2027 | 0 | 0 | 0
2027-05-01 | 2027 | 0 | 0 | 0
2027-06-01 | 2027 | 0 | 0 | 0
2027-07-01 | 2027 | 0 | 0 | 0
2027-08-01 | 2027 | 0 | 0 | 0
2027-09-01 | 2027 | 0 | 0 | 0
2027-10-01 | 2027 | 0 | 0 | 0
2027-11-01 | 2027 | 0 | 0 | 0
2027-12-01 | 2027 | 0 | 0 | 0
2028-01-01 | 2028 | 0 | 0 | 0
2028-02-01 | 2028 | 0 | 0 | 0
2028-03-01 | 2028 | 0 | 0 | 0
2028-04-01 | 2028 | 0 | 0 | 0
2028-05-01 | 2028 | 0 | 0 | 0
2028-06-01 | 2028 | 0 | 0 | 0
2028-07-01 | 2028 | 0 | 0 | 0
2028-08-01 | 2028 | 0 | 0 | 0
2028-09-01 | 2028 | 0 | 0 | 0
2028-10-01 | 2028 | 0 | 0 | 0
2028-11-01 | 2028 | 0 | 0 | 0
2028-12-01 | 2028 | 0 | 0 | 0
TOTAL |  | 1000 | 9000 | 10000 | 0 | 0
Note on F5: TRM: monthly target, entered by hand (per user). Leave it blank where you have no target.

## Phased Budget
Phased Budgeted – calculation grid (no inputs)
Budgeted × weight(k) ÷ Σ remaining weights, for project months after the Current Month only.
# | Project Name | Starting Month | Duration | Budgeted | Σ remaining weights | Equal weights? | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
1 | Example Project (slide) | 2026-10-01 | 5 | 9000 | 8 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  |  |  | 0 | 0 | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  |  | 9000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0